## Sheet1
Pillar | Critical activities (desired timeframe for completion shaded light yellow) | 3m | 2m | 4wk | 2wk | 1wk
1. PLANNING | 1.1 District-level operational plans (including a list of focal points) developed for 1) vaccine supply and cold chain, 2) waste management, 3) safety monitoring, 4) training, 5) social mobilization and communication and 6) reporting and data analysis
1. PLANNING | 1.2 Coordination team established at district level
1. PLANNING | 1.3 Microplans finalized (including identification of target populations, health facilities, community health volunteers, hard-to-reach populations etc.)
1. PLANNING | 1.4 Funds received for all planned activities
1. PLANNING | 1.5 Funds distributed for all planned activities appropriately
2. TRAINING | 2.1 Health workers trained
2. TRAINING | 2.2 Community health volunteers trained
2. TRAINING | 2.3 Supervisors identified and trained
3.MONITORING & SUPERVISION | 3.1 Supervision plan developed including visit dates, health facilities and names of supervisors for pre-launch readiness assessment and post-introduction visits
3.MONITORING & SUPERVISION | 3.2 Monitoring tools received at district level
3.MONITORING & SUPERVISION | 3.3 Monitoring tools delivered at health facilities
4.VACCINE, COLD CHAIN & LOGISTICS | 4.1 Sufficient cold-chain capacity and contingency plans for malaria vaccine storage confirmed
4.VACCINE, COLD CHAIN & LOGISTICS | 4.2 Waste management assessment completed and action taken for any gaps
4.VACCINE, COLD CHAIN & LOGISTICS | 4.3 Vaccines and supplied delivered in adequate quantitiy to health facilities;
4.VACCINE, COLD CHAIN & LOGISTICS | - 4.4a Vaccines
4.VACCINE, COLD CHAIN & LOGISTICS | - 4.4b 0.5ml AD syringes
4.VACCINE, COLD CHAIN & LOGISTICS | - 4.4c 2ml RUP reconstitution syringes
4.VACCINE, COLD CHAIN & LOGISTICS | - 4.4d Safety boxes
4.VACCINE, COLD CHAIN & LOGISTICS | - 4.4e (If relevant) additional commodities (such as vitamin A, deworming, insecticide-treated bed nets etc.)
5. ADVOCACY, SOCIAL MOBILIZATION & COMMUNICATION | 5.1 ACSM materials delivered to health facilities
5. ADVOCACY, SOCIAL MOBILIZATION & COMMUNICATION | 5.2. ACSM activities implemented according to the microplan
5. ADVOCACY, SOCIAL MOBILIZATION & COMMUNICATION | 5.3. Community awareness on the date and venues of malaria vaccination verified