## Sheet1
Pillar | Critical activities (desired timeframe for completion shaded light yellow) | 9-7m | 6-4m | 3m | 2m | 1m | 2wk | 1wk
1. PLANNING | 1.1 Political commitment at highest level | Yes
1. PLANNING | 1.2 Operational plan developed for malaria vaccine introduction, including target introduction date | Yes
1. PLANNING | 1.3 Introduction budget and available funding sources reviewed and potential gaps identified | Yes
1. PLANNING | 1.4 Additional funds mobilized (if needed) | No
1. PLANNING | 1.5 Malaria vaccine delivery strategy/schedule confirmed | Yes
1. PLANNING | 1.6 National Technical Working Group (TWG) established with appropriate participation, including by the national malaria control programme and malaria partners, and meeting regularly | Yes
1. PLANNING | 1.7 TWG subcommittees established: 1) technical, 2) cold chain & logistics, 3) advocacy, communication and social mobilization (ACSM), and 4) monitoring and evaluation, with appropriate terms of reference (ToRs) | No
1. PLANNING | 1.8 (GAVI countries) Vaccine Introduction Grant (VIG) funds received by MOH | No
1. PLANNING | 1.9 Briefings with TWG, MOH and other sub-natioal stakeholders on geographical areas for roll-out held | No
1. PLANNING | 1.10 Gavi additional TA partner confirmed and introduced to MOH/TWG | No
1. PLANNING | 1.11 Funds available to the district level for operational costs | No
1. PLANNING | 1.12 Microplans developed at district level | No
2. TRAINING | 2.1 Training plan and materials developed and adapted to local contexts | No
2. TRAINING | 2.2 Training materials distributed to all districts | No
2. TRAINING | 2.3 Training of trainers carried out at national and sub-national level | No
2. TRAINING | 2.4 Training of health workers, community health volunteers and supervisors carried out | No
3.MONITORING & SUPERVISION | 3.1. A set of monitoring indicators for malaria vaccine developed and reviewed | No
3.MONITORING & SUPERVISION | 3.2 Monitoring tools updated to include malaria vaccine (vaccination card, monitoring charts, tally sheets, reporting forms, registers, default-tracing register, supervisory checklists, AEFI reporting forms etc.) | Yes
3.MONITORING & SUPERVISION | 3.3 Monitoring tools printed and distributed to health facilities | Yes
3.MONITORING & SUPERVISION | 3.4 Pre-introduction supervisory visits conducted to assess readiness for introduction | Yes
4.VACCINE, COLD CHAIN & LOGISTICS | 4.1 Vaccine licensure/registration granted by NRA | Yes
4.VACCINE, COLD CHAIN & LOGISTICS | 4.2 Confirmation of vaccine delivery date received | Yes
4.VACCINE, COLD CHAIN & LOGISTICS | 4.3 Integration (if relevant): additional commodities (e.g. deworming, insecticide-treated bed nets etc) ordered to be available for introduction | Yes
4.VACCINE, COLD CHAIN & LOGISTICS | 4.4 Cold-chain assessment completed at all levels and action taken for any gaps | Yes
4.VACCINE, COLD CHAIN & LOGISTICS | 4.5 Waste management assessment completed and action taken for any gaps | Yes
4.VACCINE, COLD CHAIN & LOGISTICS | 4.6 Tracking/monitoring system for vaccine supply management in place | Yes
4.VACCINE, COLD CHAIN & LOGISTICS | 4.7 Vaccine and injection supplies received and distributed to regional and district level | Yes
5. ADVOCACY, SOCIAL MOBILIZATION & COMMUNICATION | 5.1 A budgeted national plan for advocacy, social mobilization and communication developed and finalized | Yes
5. ADVOCACY, SOCIAL MOBILIZATION & COMMUNICATION | 5.2 ACSM materials developed, validated and translated (e.g. pamphlets, leaflets, t-shirts, caps, banners, posters, jingles, radio/TV announcements, social media etc.) | Yes
5. ADVOCACY, SOCIAL MOBILIZATION & COMMUNICATION | 5.3 Risk communication and management plan developed and key actors briefed and trained (spokesperson training) | No
5. ADVOCACY, SOCIAL MOBILIZATION & COMMUNICATION | 5.4 Communication plan implemented and advocacy & planning meetings held with partners and stakeholders (Ministries; NGOs, professional / scientific societies, media/journalists & civil society groups) | No
5. ADVOCACY, SOCIAL MOBILIZATION & COMMUNICATION | 5.5 ACSM materials distrivuted to health facilities, community leaders, communities and other key stakeholders | No
5. ADVOCACY, SOCIAL MOBILIZATION & COMMUNICATION | 5.6 Launch ceremony for malaria vaccine introduction planned | Yes